## Project Plan
PROJECT GANTT CHART — Software Platform Launch ¦ Jan 2025 – Oct 2025
Duration: 10 Months (Jan 6, 2025 – Oct 31, 2025) ¦ 43 Weeks ¦ Last Updated: Mar 2025
[6 empty] | Jan 2025 |  |  |  | Feb 2025 |  |  |  | Mar 2025 |  |  |  |  | Apr 2025 |  |  |  | May 2025 |  |  |  | Jun 2025 |  |  |  |  | Jul 2025 |  |  |  | Aug 2025 |  |  |  | Sep 2025 |  |  |  |  | Oct 2025
# | Task / Deliverable | Owner | Start | End | % Done | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43
Phase 1: Planning & Discovery
1 | Project Kickoff | John Smith | 06 Jan 2025 | 13 Jan 2025 | 100%
2 | Requirements Gathering | Sarah Lee | 13 Jan 2025 | 10 Feb 2025 | 100%
3 | Stakeholder Interviews | John Smith | 13 Jan 2025 | 03 Feb 2025 | 100%
4 | Scope & Risk Assessment |  | 03 Feb 2025 | 24 Feb 2025 | 80%
5 | Project Charter Sign-off |  | 24 Feb 2025 | 03 Mar 2025 | 0%
Phase 2: Design
6 | System Architecture |  | 24 Feb 2025 | 07 Apr 2025 | 100%
7 | UI/UX Wireframes |  | 03 Mar 2025 | 14 Apr 2025 | 75%
8 | Database Schema Design |  | 17 Mar 2025 | 14 Apr 2025 | 60%
9 | Design Review & Approval |  | 14 Apr 2025 | 21 Apr 2025 | 0%
Phase 3: Development
10 | Backend Development |  | 14 Apr 2025 | 21 Jul 2025 | 40%
11 | Frontend Development |  | 21 Apr 2025 | 21 Jul 2025 | 25%
12 | API Integration |  | 09 Jun 2025 | 04 Aug 2025 | 10%
13 | Database Implementation |  | 14 Apr 2025 | 23 Jun 2025 | 55%
14 | Unit Testing |  | 23 Jun 2025 | 11 Aug 2025 | 0%
15 | Code Review & Refactor |  | 14 Jul 2025 | 11 Aug 2025 | 0%
16 | Dev Sprint Sign-off |  | 11 Aug 2025 | 18 Aug 2025 | 0%
Phase 4: Testing & QA
17 | Integration Testing |  | 11 Aug 2025 | 15 Sep 2025 | 0%
18 | User Acceptance Testing |  | 25 Aug 2025 | 29 Sep 2025 | 0%
19 | Performance Testing |  | 25 Aug 2025 | 15 Sep 2025 | 0%
20 | Bug Fixing |  | 08 Sep 2025 | 06 Oct 2025 | 0%
21 | QA Sign-off |  | 06 Oct 2025 | 13 Oct 2025 | 0%
Phase 5: Deployment & Launch
22 | Staging Deployment |  | 06 Oct 2025 | 20 Oct 2025 | 0%
23 | Production Deployment |  | 20 Oct 2025 | 27 Oct 2025 | 0%
24 | Go-Live |  | 27 Oct 2025 | 03 Nov 2025 | 0%
25 | Hypercare Support |  | 03 Nov 2025 | 27 Oct 2025 | 0%
LEGEND
Completed (100%)
In Progress
Not Started
Milestone / Sign-off
Critical / At-Risk